Scrum-Based Requirements Collection

Centralized Routing Management System

| Course | Informatics for Telecommunications |
| --- | --- |
| Program | Electronic Engineering and Telecommunications |
| Project | Centralized Routing System |
| Team name | NetCore Team |
| Team members | Eider Daniel Fernandez — Developer + Tester, Isabella Perez Hoyos — Documenter + Developer |
| Professor | Oscar Mauricio Caicedo Rendon |
| Start date | April 25, 2026 |
| Final date | June 17, 2026 |
| Version | 1.0 |

# 1. Product Vision

This project develops a software-based centralized routing system where router applications communicate with a central controller application. The controller maintains the full network topology, computes optimal routes using Dijkstra's algorithm, generates forwarding tables for each router, and distributes them securely. All communication between the controller and routers uses TCP with TLS encryption and JSON-formatted messages.

# 2. Product Goal

Develop a centralized routing system in Python composed of a controller application (Control Plane) and multiple router applications (Data Plane). The controller computes routing tables from the network topology using Dijkstra's algorithm and sends them to the router applications using TCP, JSON, and TLS-based secure communication. Each router applies Longest Prefix Matching (LPM) to forward simulated packets. The system includes periodic heartbeat-based fault detection and route recalculation for affected paths.

# 3. Stakeholders

| Stakeholder | Role | Interest |
| --- | --- | --- |
| Professor | Evaluator and project guide | Verify correct application of programming, software engineering, and networking concepts |
| Eider Daniel Fernandez | Developer + Tester | Design, implement, and test the system components |
| Isabella Perez Hoyos | Documenter + Developer | Document the system design, requirements, and design, implement the system components |
| Controller application | System component | Compute and distribute routing information to all routers |
| Router application | System component | Send local topology information and receive and apply routing tables |
| Network administrator | User | Monitor the network and validate routing behavior |

# 4. User Story Format

Use the following format for each requirement:

As a [type of user], I want [functionality], so that [benefit].

# 5. Functional Requirements Backlog

| ID | User story | Priority | Acceptance criteria | Sprint | Status |
| --- | --- | --- | --- | --- | --- |
| FR-01 | As a router application, I want to register with the controller so that the controller can identify me in the network. | High | The router sends ID, IP, and port. The controller stores the router information in its database. | Sprint 1 | Pending |
| FR-02 | As a router application, I want to send neighbor information to the controller so that the controller can build the network topology. | High | The router sends neighbors and link costs. The controller updates the topology graph. | Sprint 1 | Pending |
| FR-03 | As a controller, I want to store the network topology so that routing algorithms can be executed. | High | The topology is stored as a weighted graph. Nodes are routers, edges are links with costs. | Sprint 1 | Pending |
| FR-04 | As a controller, I want to compute shortest paths so that optimized routing tables can be generated. | High | The controller computes best paths from each router to every destination using Dijkstra's algorithm. | Sprint 2 | Pending |
| FR-05 | As a controller, I want to generate a routing table for each router so that each router knows the next hop for every destination. | High | Each table contains destination prefix, prefix length, next hop, and cost. Longest Prefix Matching is applied. | Sprint 2 | Pending |
| FR-06 | As a router application, I want to receive my routing table from the controller so that I can make forwarding decisions. | High | The router receives the table via TCP+TLS, stores it in local memory or lightweight local persistence, and applies LPM for packet forwarding. | Sprint 2 | Pending |
| FR-07 | As a router application, I want to display my routing table so that the administrator can verify the routing information. | Medium | The routing table is shown in the command-line interface with destination, next hop, prefix length, and cost. | Sprint 2 | Pending |
| FR-08 | As a network administrator, I want to simulate a link cost change so that I can observe route recalculation. | Medium | The controller recalculates affected routing tables after the update. | Sprint 3 | Pending |
| FR-09 | As a controller, I want to log important events so that system execution can be analyzed. | Low | Registration, topology updates, route computation, table delivery, and fault events are logged in the database. | Sprint 3 | Pending |
| FR-10 | As a controller, I want to encrypt all communication with TLS so that configuration messages travel securely between components | High | All controller-router TCP connections use TLS through standard Python libraries. Unauthenticated or invalid-token connections are rejected | Sprint 3 | Pending |
| FR-11 | As a controller, I want to detect when a router stops responding so that I can recalculate affected routes automatically | Medium | The controller sends a heartbeat periodically (for example, every 5 seconds). After 3 consecutive missed responses, the router is marked as down and affected routes are recalculated. | Sprint 3 | Pending |
| FR-12 | As a router application, I want to maintain a FIFO queue with a configurable maximum size so that I can manage packet traffic under load. | High | The router queues incoming packets in FIFO order. When the queue is full, new packets are discarded (tail drop). Queue size is configurable. | Sprint 3 | Pending |
| FR-13 | As a controller, I want to receive periodic metrics from each router so that I can monitor the network state from a central point. | Low | Each router sends a METRICS JSON message periodically (for example, every 30 seconds) with queue size, packets forwarded, and packets discarded. | Sprint 3 | Pending |

# 6. Non-Functional Requirements Backlog

| ID | Requirement | Description | Priority | Acceptance criteria |
| --- | --- | --- | --- | --- |
| NFR-01 | Python implementation | The system must be implemented in Python. | High | All main applications are Python programs. |
| NFR-02 | Modularity | Separate controller logic, router logic, communication logic, and routing algorithm logic. | High | Code is organized into modules, classes, or packages following MVC+DAO pattern. |
| NFR-03 | Command-line execution | The system must be operated from the terminal. | High | Controller and routers can be started from the command line. |
| NFR-04 | JSON messages | Messages between routers and controller must use JSON. | High | All exchanged messages are valid JSON objects. |
| NFR-05 | Reliability | The system should handle invalid messages without crashing. | Medium | Invalid messages generate error responses or logs. |
| NFR-06 | Scalability | The system should support at least four router applications. | Medium | The controller manages four or more routers correctly. |
| NFR-07 | Maintainability | The code should be readable and documented. | Medium | Functions and classes include meaningful names and comments. |
| NFR-08 | Testability | The system should include tests for the main requirements. | Medium | Test cases are documented and executed. |
| NFR-09 | Security — TLS | All communication between the controller and routers must be protected using TLS through standard libraries. | High | No message is transmitted without TLS. Connections without a valid token are rejected |
| NFR-10 | Availability | The system must detect and handle router failures automatically within the configured monitoring cycle. Three consecutive failures mark the router as down and trigger route recalculation. | Medium | Heartbeat. Three consecutive failures mark the router as down and trigger route recalculation. |

# 7. Product Backlog

| Backlog ID | Requirement ID | Task | Responsible student | Estimated effort | Sprint | Status |
| --- | --- | --- | --- | --- | --- | --- |
| PB-01 | FR-01 / NFR-01 / NFR-02 | Set up Python project (virtual environment, requirements.txt, folder structure: controller/, router/, shared/, tests/, docs/). Define all JSON message schemas (AUTH, UPDATE_TABLE, METRICS, HEARTBEAT, PACKET_SIM, ROUTER_DOWN). | Eider / Isabella | 6 h | Sprint 1 | Pending |
| PB-02 | FR-01 / NFR-03 | Set up TCP socket server (controller) and client (router). Implement router registration: router sends ID, IP, and port via JSON; controller stores it in database. | Isabella | 6 h | Sprint 1 | Pending |
| PB-03 | FR-02 / FR-03 | Implement neighbor information exchange (JSON with router ID, neighbor list, costs) and topology storage as a weighted graph in the controller. | Eider | 6 h | Sprint 1 | Pending |
| PB-04 | NFR-01 | Create and initialize controller database (tables: routers, enlaces, rutas_calculadas, eventos, metricas_globales). | Isabella | 3 h | Sprint 1 | Pending |
| PB-05 | FR-04 / FR-05 | Implement Dijkstra's algorithm on the topology graph. Generate routing table per router (destination prefix, prefix length, next hop, cost). | Eider | 8 h | Sprint 2 | Pending |
| PB-06 | FR-06 / NFR-01 | Send routing table from controller to each router via TCP+JSON. Router stores the forwarding table in local memory or lightweight local persistence. | Isabella | 6 h | Sprint 2 | Pending |
| PB-07 | FR-06 / FR-07 | Implement LPM forwarding logic in router (ORDER BY prefix length DESC, match first entry). Display routing table in CLI in formatted table view. | Eider / Isabella | 6 h | Sprint 2 | Pending |
| PB-08 | FR-05 / NFR-07 | Simulate packet forwarding hop-by-hop from source router to destination IP showing full path. Add docstrings and comments to all Sprint 1 and 2 modules. | Eider / Isabella | 6 h | Sprint 2 | Pending |
| PB-09 | FR-10 / NFR-09 | Integrate TLS over existing TCP sockets using Python standard SSL/TLS libraries. Implement token-based authentication. | Isabella | 8 h | Sprint 3 | Pending |
| PB-10 | FR-11 / NFR-10 | Implement heartbeat: controller pings each router every constantly. After 3 consecutive failures, mark router as down, log event, and recalculate affected routes. | Eider | 5 h | Sprint 3 | Pending |
| PB-11 | FR-08 | Implement link cost change simulation: administrator triggers update from CLI, controller recalculates Dijkstra and redistributes affected forwarding tables. | Eider | 4 h | Sprint 3 | Pending |
| PB-12 | FR-12 / FR-13 | Implement FIFO queue with configurable max size and tail drop in router. Implement periodic METRICS message (every 30 seconds) and controller storage in metricas_globales. | Isabella | 5 h | Sprint 3 | Pending |
| PB-13 | FR-09 / NFR-08 | Finalize event logging for all system events. Write, execute, and automate test cases for all functional requirements. | Eider | 6 h | Sprint 3 | Pending |
| PB-14 | All | Final integration test with 4-5 router topology. Validate all FR and NFR acceptance criteria. Push complete project to GitHub repository. | Eider / Isabella | 4 h | Sprint 3 | Pending |

# 8. Sprint Planning Template

## Sprint 1 — Communication Base and Topology

| Field | Description |
| --- | --- |
| Sprint number | 1 |
| Sprint goal | Establish the project structure, set up TCP communication between controller and routers, implement router registration and topology building. |
| Start date | April 25, 2026 |
| End date | May 12, 2026 |
| Team members | Eider Daniel Fernandez, Isabella Perez Hoyos |

| Task ID | Requirement ID | Task description | Responsible | Estimated time | Status |
| --- | --- | --- | --- | --- | --- |
| T-01 | PB-01 | Set up Python project, folder structure and define all JSON message schemas. | Eider / Isabella | 6 h | Pending |
| T-02 | PB-02 | Set up TCP socket server and client. Implement router registration with JSON and controller database storage. | Eider | 6 h | Pending |
| T-03 | PB-03 | Implement neighbor information exchange and topology storage as weighted graph. | Isabella | 6 h | Pending |
| T-04 | PB-04 | Create and initialize controller database with all required tables. | Isabella | 3 h | Pending |

## Sprint 2 — Dijkstra, Routing Tables and Packet Forwarding

| Field | Description |
| --- | --- |
| Sprint number | 2 |
| Sprint goal | Implement Dijkstra's algorithm, generate and distribute forwarding tables, implement LPM in routers, and simulate packet forwarding hop-by-hop. |
| Start date | May 13, 2026 |
| End date | May 26, 2026 |
| Team members | Eider Daniel Fernandez, Isabella Perez Hoyos |

| Task ID | Requirement ID | Task description | Responsible | Estimated time | Status |
| --- | --- | --- | --- | --- | --- |
| T-05 | PB-05 | Implement Dijkstra's algorithm and generate routing table per router. | Eider | 8 h | Pending |
| T-06 | PB-06 | Send routing table from controller to router. Router stores it in local database. | Isabella | 6 h | Pending |
| T-07 | PB-07 | Implement LPM forwarding logic and display routing table in router CLI. | Eider / Isabella | 6 h | Pending |
| T-08 | PB-08 | Simulate packet forwarding hop-by-hop. Add docstrings to all Sprint 1 and 2 modules. | Eider / Isabella | 6 h | Pending |

## Sprint 3 — Security, Fault Detection, Metrics and Final Delivery

| Field | Description |
| --- | --- |
| Sprint number | 3 |
| Sprint goal | Add TLS encryption, token authentication, heartbeat fault detection, FIFO queue, metrics reporting, full event logging, automated tests, and final system integration with five-router topology. |
| Start date | May 27, 2026 |
| End date | June 17, 2026 |
| Team members | Eider Daniel Fernandez, Isabella Perez Hoyos |

| Task ID | Requirement ID | Task description | Responsible | Estimated time | Status |
| --- | --- | --- | --- | --- | --- |
| T-09 | PB-09 | Integrate TLS over TCP sockets using standard libraries. Implement token authentication. | Eider | 8 h | Pending |
| T-10 | PB-10 | Implement heartbeat every 5 seconds. Mark router down after 3 missed responses. | Isabella | 5 h | Pending |
| T-11 | PB-11 | Implement link cost change simulation and route redistribution | Eider | 4 h | Pending |
| T-12 | PB-12 | Implement FIFO queue with tail drop and periodic METRICS reporting. | Isabella | 5 h | Pending |
| T-13 | PB-13 | Finalize event logging. Write, execute and automate test cases for the core requirements. | Eider | 6 h | Pending |
| T-14 | PB-14 | Final integration test with 4-5 router topology. Push to GitHub. | Eider / Isabella | 4 h | Pending |

# 9. Definition of Done

| Criterion | Completed? |
| --- | --- |
| The functionality is implemented in Python |  |
| The code was tested successfully |  |
| Expected input and output were documented |  |
| Acceptance criteria were met |  |
| The code was integrated with the rest of the system without breaking existing functionality. |  |
| The functionality was demonstrated to the professor |  |
| The relevant database tables were updated or verified. |  |